## WBS with Gantt Chart BLANK
Work Breakdown Structure With Gantt Chart
Project Title | Expense Tracker with Receipt OCR
Team Leader | Mao Sovan
Team member | Heng Dararithy, Ly Monika
Date | 22/09/2025 | [5 empty] | Phase One |  |  |  |  | Phase Two | [9 empty] | Phase Three
WBS Number | Task Title | Task Owner | Start Date | End Date | Duration | % of Task Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7
[7 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
1 | Project Planning
1.1 | Define project scope and objectives | Dararithy | 2025-09-17 | 2025-09-18 | 2 | 100%
1.2 | Identify datasets and tools | Dararithy | 2025-09-17 | 2025-09-18 | 2 | 90%
1.3 | Assign team roles and responsibilities | Sovan | 2025-09-17 | 2025-09-22 | 4 | 90% | bar: Week 1 M to Week 2 M
1.4 | Create project timeline and milestones | Sovan | 2025-09-18 | 2025-09-22 | 3 | 90% | bar: Week 1 M to Week 2 M
2 | Dataset Preparation
2.1 | Download and review Kaggle datasets | Dararithy | 2025-09-22 |  | 1 | 50% | bar: Week 1 M to Week 2 M
2.2 | Select sample receipts for testing | Dararithy | 2025-09-22 |  | 1 | 50% | bar: Week 1 M to Week 2 M
2.3 | Organize sample_receipts for OCR testing | Dararithy | 2025-09-22 |  | 1 | 50% | bar: Week 1 M to Week 2 M
3 | Core Development
3.1 | Expense Tracker Module
3.1.1 | Design expense data structure (DataFrame) | Monika |  |  |  | 0%
3.1.2 | Implement add_expense() function | Monika |  |  |  | 0%
3.1.3 | Implement get_summary() | Monika |  |  |  | 0%
3.1.4 | get_monthly_summary() | Monika |  |  |  | 0%
3.1.5 | Test manual expense logging | Monika |  |  |  | 0%
3.2 | OCR Module
3.2.1 | Preprocess receipt images | Sovan |  |  |  | 0%
3.2.2 | Apply easyOCR for text extraction | Sovan |  |  |  | 0%
3.2.3 | Implement regex parsing (date, vendor, amount) | Sovan |  |  |  | 0%
3.2.4 | Predict category | Sovan |  |  |  | 0%
3.3 | Streamlit UI
3.31 | Build sidebar navigation (menu options) | Dararithy |  |  |  | 0%
3.32 | Add manual expense entry form | Dararithy |  |  |  | 0%
3.33 | Add receipt upload & OCR integration | Dararithy |  |  |  | 0%
3.34 | Add expense table view and Charts | Dararithy |  |  |  | 0%
4 | Integration & Testing
4.1 | Connect tracker + OCR modules into Streamlit app | Dararity |  |  |  | 0%
4.2 | Perform end-to-end testing with sample receipts | Dararity |  |  |  | 0%
4.3 | Verify OCR accuracy and allow user corrections | Dararity |  |  |  | 0%
4.4 | Debug and optimize code performance | Dararity |  |  |  | 0%
5 | Documentation & Packaging
5.1 | Write project documentation (topic, dataset, scope) | Dararithy | 2025-09-18 | 2025-09-22 | 3 | 80% | bar: Week 1 M to Week 2 M
5.2 | Create WBS diagram/table and progress tracker | Sovan | 2025-09-18 | 2025-09-22 | 3 | 90% | bar: Week 1 M to Week 2 M
5.3 | Take screenshots of working app | Monika |  |  |  | 0%
5.4 | Prepare requirements.txt | Sovan | 2025-09-22 |  | 1 | 50% | bar: Week 1 M to Week 2 M
5.5 | Bundle source code, dataset, and docs into ZIP | Dararithy |  |  |  | 0%
6 | Final Review & Submission
6.1 | Team code review and testing session | All |  |  |  | 0%
6.2 | Validate deliverables against objectives | Dararithy |  |  |  | 0%
6.3 | Submit ZIP file with all required components | Sovan |  |  |  | 0%